## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
BUG-01 | Niharika | 2026-12-29 | Merge conflict: logic overwrite in app.py | sprint 2 | Niharika | Maintainability | Restricted main branch;enforced 7-branch workflow | 2026-01-05 | Closed | Process updated
BUG-02 | Gauri joshi | 2026-12-22 | Encoding error: CSVs with special charts failing | sprint 2 | Gauri joshi | Logical | Added latin-1 fallback in utils.py. | 2026-12-22 | Closed | critical fix
BUG-03 | Khushi bhandari | 2026-12-26 | Visuals: bar charts overlapping | sprint 3 | Kriti gautam | User Interface | Adjusted figure size and rotation using matplotlib | 2026-12-27 | Closed | Verified
BUG-04 | Vanshika jain | 2026-12-27 | Analysis: complex filters causing slow load | sprint 3 | Vinay manda | Standards | Optimization aasistance from AI tools(claude) | 2026-12-28 | Closed | Optimizes
BUG-05 | Chandana BC | 2026-12-28 | UI Glitch: sidebar overlapping text | sprint 3 | Laasya kadali | User Interface | Applied custom CSS media queries | 2026-12-28 | Closed | Verified
BUG-06 | Niharika raut | 2026-12-28 | Map visibility: map not loading for certain states | sprint 4 | Niharika raut | Maintainability | Swapped broken geoJSON with valid open source files | 2026-12-02 | Closed | Fixed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others